## Sheet1
| weeks | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 | 10 | 11
|  | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables | Effort | deadline | beginTime | Delivery standards | deliverables
Wang(王子越) | [6 empty] | Learning document | 10h | 3/19 | 3/05 | Technical report | The code Page prototype of web | 7h | 3/26 | 3/19 | interactive interface | the code of the first version of the site page | 7h | 4/02 | 3/26 | Image upload | the documentation of Web framework interface test | 7h | 4/09 | 4/02 | At least 2 bugs | The instructions of bug repaired | 4h | 4/16 | 4/10 | The test bug has been fixed | the code of the second version of the site page | 7h | 4/23 | 4/17 | search and query functions | the document of Test and optimize | 7h | 5/30 | 4/24
King(车金刚) | [6 empty] | Learning document | 10h | 3/19 | 3/05 | Technical report | Website framework construction progress document | 7h | 3/26 | 3/19 | The basic framework is completed | the code of Website background framework and interface | 7h | 4/02 | 3/26 | Ability to manipulate data in a database | the documentation of site page test | 7h | 4/09 | 4/02 | At least 3 bugs | The instructions of bug repaired | 4h | 4/16 | 4/10 | The test bug has been fixed | the code of Website interface | 7h | 4/23 | 4/17 |  | the document of Test and optimize | 7h | 5/30 | 4/24
Yu(俞力) | [6 empty] | Learning document | 10h | 3/19 | 3/05 | Technical report | the code of Image processing | 7h | 3/26 | 3/19 | Capable of image denoising | the code of Word recognition processing | 7h | 4/02 | 3/26 | The ratio of Character recognition is up to 70% | the documentation of Database interface test | 7h | 4/09 | 4/02 | At least 2 bugs | The instructions of bug repaired | 4h | 4/16 | 4/10 | The test bug has been fixed | the code of Optimizing text recognition | 7h | 4/23 | 4/17 |  | the document of Test and optimize | 7h | 5/30 | 4/24
Mars(涂晓招) | [6 empty] | Learning document | 10h | 3/19 | 3/05 | Technical report | Data capture document | 7h | 3/26 | 3/19 | The data includes 300 tang poems and basic song lyrics |  | 7h | 4/02 | 3/26 |  | the documentation of Word recognition interface test | 7h | 4/09 | 4/02 | At least 2 bugs | The instructions of bug repaired | 4h | 4/16 | 4/10 | The test bug has been fixed |  | 7h | 4/23 | 4/17 |  | the document of Test and optimize | 7h | 5/30 | 4/24
all numbers |  | Project plan | 7h | 3/12 | 3/05 | Have general design and requirements analysis | detailed design | 7h | 3/19 | 3/12 | Interface design, database field design and Detailed design of the project | [15 empty] | all of the code and the plans of the next | 3h | 4/16 | 4/10 | detail plans | [10 empty] | all documents and all code